## Sheet1
S. No. | Task Name | Sub Task1 | Sub Task 2 | Priority | Expected Days To Complete | Status
1 | Read SDP32 correctly, (Real time mean value) |  |  | 1 | 3 | Completed
2 | Calculate the flow rate, timimg libarry is needed, Counter Management |  |  | 1 | 3
3 | Timming library for timing management(to manage the volume) |  |  | 2 | 2
4 | PID |  |  | 3 | 4
5 | Motor Control |  |  | 3 | 4
6 | GUI Linking (Sample Manage, Sequence manage, Calibrartion) |  |  | 6 | 5
7 | Calibration Task |  |  | 5 | 5
8 | Memory saving (Non Volatile Storage (NVS)) |  |  | 4 | 4
9 | Battery Management |  |  | 11 | 2
10 | Buzzer management |  |  | 12 | 1
11 | LED Management |  |  | 13 | 1
12 | Sample management |  |  | 7 | 2
13 | Data Export Management |  |  | 17 | 4
14 | Wakeup Management |  |  | 8 | 1
15 | Screen parameters management (Back light, variables) |  |  |  | 2
16 | Time & Date Management |  |  | 9 | 1
17 | Update Management |  |  | 16 | 4
18 | Pump Parameter Management (Serial Number, Factory Settings, Language management & setting Management) |  |  | 14 | 5
19 | Alert Management (Battery Low, Sensor Problem, flow problem, displacement , flow limit (metrology reminder limit) 10 |  |  | 10 | 10
ESP_UPM work in progress signal and record alert
- device is mooved or big shock,
- device have GPS coordinate change,
- Diff. Press. high or decrease,
- user try to put a wrong code,
- cutting power supply on-grid
- low battery
ESP_UPM work in progress critical alert
- not enough power to finish
- power grid disconnected
- flip down
- low battery when no power grid connect
- Diff. Press. too high
- movement far from xx cm
20 | User Management (Different password management******, Logo setting, ) |  |  | 15 | 5
* name
* code password
* acces advanced setting
* laboratory code access
21 | Mode Management
|  | * Mode storage : device is totally off, just wake up when shock or movement happened, to avoid stolen, the device will connect to network to send the state everyday ( state is : position, battery state, and update all setting and parameter file ), |  | 6 | 10
* Mode wait : during this mode device is waiting for the job already programmed by user, led is blinking yellow, screen is off and the pump is locked another user can’t stop the program.
* Mode shut down/low power:led color depend on problem during work (blinking green: no problem, blinking orange: problem during sample , same as storage mode except scan wifi every 30 sec,
* Mode low bat / no power:led is double quick blinking red, this mode is strictly during sample
* Mode etalon in progress: led is blinking Cyan, this mode is enable during metrology validation test
* Mode metrology: led is Cyan, this mode is enable during metrology is enable
* Mode enable: led is green , all is on device is ready for a new programing work, wifi is enable fully.
* mode busy/sample in progress: led is blinking slow blue, work is in progress , scan wifi every 30 sec